## Payments Backlog
Issue Type | Summary | Epic Name | Epic Link | Priority | Story Points | Sprint | Labels | Status | Description
Epic | PAY-F01 — Payment Initiation & Paystack Checkout | PAY-F01 — Payment Initiation & Paystack Checkout | PAY-F01 | Highest |  | Sprint 1 | PAY-F01 phase-1 srs-must initiate paystack | Partial | SRS-PAY-F01: Consuming systems POST /v1/payments/initiate with a unique PAY-{SYSTEM}-{hex16} reference; gateway calls Paystack /transaction/initialize and returns a hosted checkout authorization_url. Idempotent on reference.
Story | F01-1 POST /v1/payments/initiate creates Payment and returns Paystack checkout URL | PAY-F01 — Payment Initiation & Paystack Checkout | PAY-F01 | Highest | 5 | Sprint 1 | PAY-F01 phase-1 srs-must F01-1 initiate | Done | SRS-PAY-F01 / F01-1: PaymentService.initiate() (app/services/payment_service.py:39) persists a Payment row status=pending and calls PaystackClient.initialize_transaction(); endpoint initiate_payment() at app/api/v1/payments.py:47 returns 201 with authorization_url/access_code.
Story | F01-2 Idempotent re-submission of an existing reference returns the same checkout URL | PAY-F01 — Payment Initiation & Paystack Checkout | PAY-F01 | High | 3 | Sprint 1 | PAY-F01 phase-1 srs-must F01-2 idempotency | Done | SRS-PAY-F01: initiate() checks for an existing Payment by reference and returns the stored paystack_authorization_url with HTTP 200 instead of creating a duplicate; verify 409 path when a reference exists with no checkout URL.
Story | F01-3 Validate source_system enum and positive amount on initiate | PAY-F01 — Payment Initiation & Paystack Checkout | PAY-F01 | High | 2 | Sprint 1 | PAY-F01 phase-1 srs-must F01-3 validation | Done | SRS-PAY-F01: PaymentInitiateRequest (app/schemas/payment.py:13) validators amount_positive() and valid_source_system() enforce amount>0 and source_system in {ams,nlems,nbes,evs,certification}; 422 returned on violation.
Story | F01-4 Convert GHS to pesewas (x100) when calling Paystack initialize | PAY-F01 — Payment Initiation & Paystack Checkout | PAY-F01 | Medium | 2 | Sprint 1 | PAY-F01 phase-1 srs-must F01-4 currency | Done | SRS-PAY-F01: PaystackClient.initialize_transaction() (app/services/paystack/client.py:35) multiplies the GHS Decimal amount by 100 before sending to Paystack; confirm rounding is exact for 2-dp Numeric(12,2) amounts.
Story | F01-5 Map Paystack/HTTP failures to 502 with structured error envelope | PAY-F01 — Payment Initiation & Paystack Checkout | PAY-F01 | Medium | 3 | Sprint 1 | PAY-F01 phase-1 srs-must F01-5 errors | Partial | SRS-PAY-F01: PaystackError (client.py:17) is raised on non-2xx; initiate path should surface HTTP 502 via the errors.py handlers. Add explicit timeout handling for http_timeout_seconds and assert the {detail,status_code} envelope.
Epic | PAY-F02 — Paystack Webhook Processing & Re-verification | PAY-F02 — Paystack Webhook Processing & Re-verification | PAY-F02 | Highest |  | Sprint 1 | PAY-F02 phase-1 srs-must webhook hmac reverify | Partial | SRS-PAY-F02: Public POST /v1/webhooks/paystack verifies X-Paystack-Signature (HMAC-SHA512 of the raw body), re-verifies charge.success against the Paystack API, sets status confirmed/failed, and is idempotent via the processed_webhooks table.
Story | F02-1 Verify X-Paystack-Signature HMAC-SHA512 on inbound webhook | PAY-F02 — Paystack Webhook Processing & Re-verification | PAY-F02 | Highest | 3 | Sprint 1 | PAY-F02 phase-1 srs-must F02-1 hmac | Done | SRS-PAY-F02 / F02-1: PaystackClient.verify_webhook_signature() (client.py:119) computes HMAC-SHA512 over the raw request body with PAYSTACK_SECRET_KEY using hmac.compare_digest(); invalid/missing signature returns 401 when the secret is configured.
Story | F02-2 Re-verify charge.success with Paystack /transaction/verify before confirming | PAY-F02 — Paystack Webhook Processing & Re-verification | PAY-F02 | Highest | 5 | Sprint 1 | PAY-F02 phase-1 srs-must F02-2 reverify | Done | SRS-PAY-F02 / F02-2: PaymentService.handle_webhook() (payment_service.py:108) calls PaystackClient.verify_transaction() on charge.success and only sets status=confirmed when the re-verified status is success; captures channel and paystack_transaction_id.
Story | F02-3 Idempotent webhook processing via processed_webhooks dedupe table | PAY-F02 — Paystack Webhook Processing & Re-verification | PAY-F02 | High | 3 | Sprint 1 | PAY-F02 phase-1 srs-must F02-3 idempotency | Done | SRS-PAY-F02 / F02-3: ProcessedWebhook (app/db/models.py:60) stores paystack_reference as the idempotency key; a previously processed reference short-circuits to HTTP 200 without reprocessing.
Story | F02-4 charge.failed sets status=failed and delivers no callback | PAY-F02 — Paystack Webhook Processing & Re-verification | PAY-F02 | High | 2 | Sprint 1 | PAY-F02 phase-1 srs-must F02-4 | Done | SRS-PAY-F02: handle_webhook() sets Payment.status=failed on charge.failed and does not invoke CallbackService.deliver(); all other Paystack event types are acknowledged 200 and ignored.
Story | F02-5 Harden webhook: 400 on malformed JSON and reject events when secret unset | PAY-F02 — Paystack Webhook Processing & Re-verification | PAY-F02 | Medium | 3 | Sprint 2 | PAY-F02 phase-1 srs-should F02-5 hardening | Partial | SRS-PAY-F02: paystack_webhook() (app/api/v1/webhooks.py:46) returns 400 on unparseable body; signature check is skipped when PAYSTACK_SECRET_KEY is empty (dev) — add a production guard that fails closed when the secret is absent.
Epic | PAY-F03 — Signed Callback Delivery to Consuming Systems | PAY-F03 — Signed Callback Delivery to Consuming Systems | PAY-F03 | High |  | Sprint 2 | PAY-F03 phase-1 srs-must callback hmac retry | Partial | SRS-PAY-F03: On confirmation the gateway POSTs a signed (X-Payment-Signature HMAC-SHA256) confirmation to the consuming system callback_url; delivery must be tracked and retried on transient failure.
Story | F03-1 Deliver signed HMAC-SHA256 callback to callback_url on confirmation | PAY-F03 — Signed Callback Delivery to Consuming Systems | PAY-F03 | High | 3 | Sprint 2 | PAY-F03 phase-1 srs-must F03-1 callback | Done | SRS-PAY-F03 / F03-1: CallbackService.deliver() (app/services/callback_service.py:29) builds the {payment_reference,status,source_system,channel,payer_name,timestamp} payload and signs it with X-Payment-Signature (HMAC-SHA256, CALLBACK_HMAC_SECRET) matching the AMS PaymentWebhookView.
Story | F03-2 Persist callback_delivered / callback_delivered_at on the Payment | PAY-F03 — Signed Callback Delivery to Consuming Systems | PAY-F03 | Medium | 2 | Sprint 2 | PAY-F03 phase-1 srs-must F03-2 | Partial | SRS-PAY-F03 / F03-2: Payment.callback_delivered and callback_delivered_at columns exist (models.py); wire deliver() to set them on a 2xx response so reconciliation can detect undelivered callbacks.
Story | F03-3 Retry callback delivery with exponential backoff on transient failure | PAY-F03 — Signed Callback Delivery to Consuming Systems | PAY-F03 | High | 5 | Sprint 2 | PAY-F03 phase-1 srs-must F03-3 retry | To Do | SRS-PAY-F03 / F03-3: deliver() is currently fire-and-forget — it returns False on failure with no retry (callback_service.py:29). Add a retry/queue with bounded exponential backoff and a LogoutDeliveryFailure-style audit record on permanent failure.
Story | F03-4 Manual callback redelivery admin endpoint for missed deliveries | PAY-F03 — Signed Callback Delivery to Consuming Systems | PAY-F03 | Medium | 3 | Sprint 3 | PAY-F03 phase-2 srs-should F03-4 redeliver | To Do | SRS-PAY-F03: No way to re-trigger a callback after a consuming-system outage; add POST /v1/payments/{reference}/redeliver-callback (admin) that re-runs CallbackService.deliver() for confirmed payments with callback_delivered=False.
Epic | PAY-F04 — CALS Financial Compliance Events & Hash Chain | PAY-F04 — CALS Financial Compliance Events & Hash Chain | PAY-F04 | High |  | Sprint 2 | PAY-F04 phase-1 srs-must cals audit hash-chain | Partial | SRS-PAY-F04: Every confirmed payment emits a masked financial-compliance-v1 event (serviceName=system-20-payment, financialTag=auditor-general) carrying a SHA-256 hash chain (previousHash/currentHash/sequence). CALS-forbidden fields must never be sent.
Story | F04-1 Post masked payment.confirmed financial event on charge.success | PAY-F04 — CALS Financial Compliance Events & Hash Chain | PAY-F04 | High | 3 | Sprint 2 | PAY-F04 phase-1 srs-must F04-1 cals | Done | SRS-PAY-F04 / F04-1: System17Client.report_payment() (app/services/system17.py:100) builds the payment.confirmed event and relays it; it never raises, logging on failure so audit reporting cannot break the payment path.
Story | F04-2 Strip CALS-forbidden financial fields before relay | PAY-F04 — CALS Financial Compliance Events & Hash Chain | PAY-F04 | High | 3 | Sprint 2 | PAY-F04 phase-1 srs-must F04-2 masking | Done | SRS-PAY-F04 / F04-2: _mask_pii() (system17.py:29) removes paymentAmount, transactionId, cardNumber, pan, cvv, accountNumber, iban, routingNumber; add a contract test asserting none of these keys ever appear in the relayed body.
Story | F04-3 SHA-256 hash chain with CAS chain-tip store (memory + Redis) | PAY-F04 — CALS Financial Compliance Events & Hash Chain | PAY-F04 | High | 5 | Sprint 2 | PAY-F04 phase-1 srs-must F04-3 chain-store | Done | SRS-PAY-F04 / F04-3: ChainStore Protocol with InMemoryChainStore and RedisChainStore (app/services/chain_store.py) maintains previousHash/currentHash/sequence per service via compare-and-set; report_payment() advances the tip from the GENESIS hash.
Story | F04-4 Post directly to CALS /v1/ingest/financial as documented fallback | PAY-F04 — CALS Financial Compliance Events & Hash Chain | PAY-F04 | Medium | 3 | Sprint 3 | PAY-F04 phase-2 srs-should F04-4 cals-direct | Partial | SRS-PAY-F04: README/API_REFERENCE specify POST {CALS_URL}/v1/ingest/financial, but events currently route only through the System 17 relay (relay_financial_event(), system17.py:41). Add the direct CALS path gated by CALS_ENABLED/CALS_URL with the same masking and chain.
Story | F04-5 Stand up Redis chain store in production compose and assert CAS under contention | PAY-F04 — CALS Financial Compliance Events & Hash Chain | PAY-F04 | Medium | 3 | Sprint 3 | PAY-F04 phase-2 srs-must F04-5 redis | Partial | SRS-PAY-F04: RedisChainStore exists but CHAIN_STORE defaults to memory; set CHAIN_STORE=redis in prod, point at the redis cache service, and add a concurrency test proving cas_update() rejects a stale expected tip.
Epic | PAY-F05 — Payment Status & Reconciliation API | PAY-F05 — Payment Status & Reconciliation API | PAY-F05 | High |  | Sprint 2 | PAY-F05 phase-1 srs-must status list reconcile | Partial | SRS-PAY-F05: Consuming systems reconcile via GET /v1/payments/{reference}; finance/admin dashboards list and filter payments via GET /v1/payments/ by source_system and status with pagination.
Story | F05-1 GET /v1/payments/{reference} returns status and metadata | PAY-F05 — Payment Status & Reconciliation API | PAY-F05 | High | 2 | Sprint 2 | PAY-F05 phase-1 srs-must F05-1 status | Done | SRS-PAY-F05 / F05-1: PaymentService.get_status() (payment_service.py:167) returns PaymentStatusResponse and raises 404 when the reference is unknown; used by consuming systems to reconcile a missed callback.
Story | F05-2 GET /v1/payments/ admin list with source_system/status filters | PAY-F05 — Payment Status & Reconciliation API | PAY-F05 | Medium | 3 | Sprint 2 | PAY-F05 phase-1 srs-must F05-2 list | Done | SRS-PAY-F05 / F05-2: PaymentService.list_payments() (payment_service.py:173) supports source_system and status filters with limit/offset (1-200).
Story | F05-3 Return paginated envelope (data/count/limit/offset) for the list endpoint | PAY-F05 — Payment Status & Reconciliation API | PAY-F05 | Medium | 2 | Sprint 3 | PAY-F05 phase-2 srs-should F05-3 pagination | Partial | SRS-PAY-F05 / F05-3: PaymentListResponse (schemas/payment.py) defines data/count/limit/offset but the endpoint returns a raw array (payments.py:92); switch to the envelope so dashboards get a total count.
Epic | PAY-F06 — Payment Lifecycle & Abandoned-Payment Expiry | PAY-F06 — Payment Lifecycle & Abandoned-Payment Expiry | PAY-F06 | High |  | Sprint 3 | PAY-F06 phase-2 srs-must lifecycle expiry scheduler | To Do | SRS-PAY-F06: Payment status lifecycle pending -> confirmed/failed/abandoned. A scheduled expiry job must transition stale pending payments to abandoned; no background scheduler exists today.
Story | F06-1 expire_stale_payments job marks pending checkouts abandoned after timeout | PAY-F06 — Payment Lifecycle & Abandoned-Payment Expiry | PAY-F06 | High | 5 | Sprint 3 | PAY-F06 phase-2 srs-must F06-1 expiry | To Do | SRS-PAY-F06 / F06-1: README (L172) and API_REFERENCE (L47) promise a 'future expiry job' but none exists — payments stay pending forever. Add a scheduled task (Celery/APScheduler) that sets status=abandoned for pending payments older than the configured checkout TTL.
Story | F06-2 Introduce a background scheduler/worker for periodic jobs | PAY-F06 — Payment Lifecycle & Abandoned-Payment Expiry | PAY-F06 | High | 5 | Sprint 3 | PAY-F06 phase-2 srs-must F06-2 scheduler | To Do | SRS-PAY-F06 / F06-2: requirements.txt has no Celery/APScheduler; add a worker process (reusing the redis cache service as broker) to host the expiry sweep and callback-retry queue.
Story | F06-3 Emit payment.abandoned reconciliation event/audit when a payment expires | PAY-F06 — Payment Lifecycle & Abandoned-Payment Expiry | PAY-F06 | Medium | 3 | Sprint 4 | PAY-F06 phase-2 srs-should F06-3 | To Do | SRS-PAY-F06 / F06-3: When expire_stale_payments transitions a row to abandoned, record an audit/CALS event so finance can distinguish abandoned from failed payments in reconciliation.
Epic | PAY-N01 — API Authentication, Rate Limiting & Secrets | PAY-N01 — API Authentication, Rate Limiting & Secrets | PAY-N01 | High |  | Sprint 4 | PAY-N01 phase-1 srs-must auth rate-limit secrets | Partial | SRS-PAY-N01: All /v1/payments endpoints require a pre-shared Bearer PAYMENT_API_KEY; the public webhook is HMAC-gated; abuse is bounded by rate limiting and secrets fail closed in production.
Story | N01-1 Bearer API-key auth dependency on all payment endpoints | PAY-N01 — API Authentication, Rate Limiting & Secrets | PAY-N01 | High | 3 | Sprint 4 | PAY-N01 phase-1 srs-must N01-1 api-key | Done | SRS-PAY-N01 / N01-1: require_api_key() (app/core/dependencies.py:27) validates the Authorization Bearer token against PAYMENT_API_KEY and returns 401 on mismatch; it is wired into the payments router.
Story | N01-2 Fail closed when PAYMENT_API_KEY / PAYSTACK_SECRET_KEY unset in production | PAY-N01 — API Authentication, Rate Limiting & Secrets | PAY-N01 | High | 3 | Sprint 4 | PAY-N01 phase-1 srs-must N01-2 fail-closed | To Do | SRS-PAY-N01 / N01-2: require_api_key() and webhook verification silently skip when their secrets are empty (dev convenience); add a production startup guard that raises if PAYMENT_API_KEY, PAYSTACK_SECRET_KEY or CALLBACK_HMAC_SECRET is missing.
Story | N01-3 Enforce per-source rate limiting on initiate and webhook | PAY-N01 — API Authentication, Rate Limiting & Secrets | PAY-N01 | Medium | 5 | Sprint 4 | PAY-N01 phase-2 srs-should N01-3 rate-limit | To Do | SRS-PAY-N01 / N01-3: Settings.rate_limit_enabled (config.py:40) exists but is never read; implement Redis-backed rate limiting middleware for /v1/payments/initiate and the webhook to bound abuse.
Epic | PAY-N02 — Data Persistence & Schema Migrations | PAY-N02 — Data Persistence & Schema Migrations | PAY-N02 | High |  | Sprint 4 | PAY-N02 phase-1 srs-must persistence alembic | Partial | SRS-PAY-N02: Payment and ProcessedWebhook are stored in a dedicated PostgreSQL instance; production schema changes must be applied through versioned Alembic migrations, not auto-create.
Story | N02-1 Replace Base.metadata.create_all bootstrap with Alembic migrations | PAY-N02 — Data Persistence & Schema Migrations | PAY-N02 | High | 5 | Sprint 4 | PAY-N02 phase-1 srs-must N02-1 alembic | To Do | SRS-PAY-N02 / N02-1: init_db() (app/db/base.py:19) auto-creates tables on startup and a comment notes Alembic should be used in production; add alembic.ini + env.py + an initial migration covering payments and processed_webhooks and gate it in CI.
Story | N02-2 Add indexes/constraints for reconciliation queries | PAY-N02 — Data Persistence & Schema Migrations | PAY-N02 | Medium | 2 | Sprint 4 | PAY-N02 phase-2 srs-should N02-2 indexes | Partial | SRS-PAY-N02 / N02-2: reference and paystack_reference are unique-indexed; add composite indexes on (source_system,status,created_at) to keep the admin list endpoint fast as volume grows.
Epic | PAY-N03 — Test Coverage & Contract Tests | PAY-N03 — Test Coverage & Contract Tests | PAY-N03 | High |  | Sprint 5 | PAY-N03 phase-1 srs-must testing contracts ci | To Do | SRS-PAY-N03: Beyond the 3 smoke tests, the gateway needs full coverage of the payment flow, webhook idempotency, signature verification, callback delivery, and CALS masking, plus OpenAPI contract tests in CI.
Story | N03-1 Integration tests for initiate -> webhook -> callback happy path | PAY-N03 — Test Coverage & Contract Tests | PAY-N03 | High | 5 | Sprint 5 | PAY-N03 phase-1 srs-must N03-1 integration | To Do | SRS-PAY-N03 / N03-1: tests/ contains only test_health.py (3 smoke tests). Add an end-to-end test with a mocked Paystack covering initiate, charge.success webhook, re-verification, confirmation, and signed callback delivery.
Story | N03-2 Tests for webhook idempotency and HMAC-SHA512/256 signatures | PAY-N03 — Test Coverage & Contract Tests | PAY-N03 | High | 3 | Sprint 5 | PAY-N03 phase-1 srs-must N03-2 security-tests | To Do | SRS-PAY-N03 / N03-2: No tests assert duplicate-webhook dedupe via processed_webhooks, reject a bad X-Paystack-Signature, or verify the outbound X-Payment-Signature. Add them as security regression tests.
Story | N03-3 CALS masking contract test: forbidden fields never relayed | PAY-N03 — Test Coverage & Contract Tests | PAY-N03 | Medium | 3 | Sprint 5 | PAY-N03 phase-1 srs-must N03-3 cals-contract | To Do | SRS-PAY-N03 / N03-3: Add a test that captures the relayed System 17/CALS body and asserts none of the eight forbidden financial fields appear, and that previousHash/currentHash/sequence advance correctly.
Story | N03-4 Wire the pytest acceptance marker into CI with real scenarios | PAY-N03 — Test Coverage & Contract Tests | PAY-N03 | Medium | 2 | Sprint 5 | PAY-N03 phase-2 srs-should N03-4 acceptance | To Do | SRS-PAY-N03 / N03-4: pyproject.toml defines an 'acceptance' marker but no acceptance tests exist; author System 17 relay acceptance scenarios and run them as a separate CI stage.
Epic | PAY-N04 — Observability, Deployment & Operations | PAY-N04 — Observability, Deployment & Operations | PAY-N04 | Medium |  | Sprint 6 | PAY-N04 phase-2 srs-should observability deploy | Partial | SRS-PAY-N04: CI builds and deploys the gateway image; production needs structured metrics, health/readiness probes, and alerting on Paystack/CALS failures and stuck pending payments.
Story | N04-1 CI pipeline: pytest + ruff + bandit, GHCR image, VPS deploy | PAY-N04 — Observability, Deployment & Operations | PAY-N04 | Medium | 3 | Sprint 6 | PAY-N04 phase-1 srs-must N04-1 ci | Done | SRS-PAY-N04 / N04-1: .github/workflows/ci.yml runs the test job (Postgres+Redis services, ruff, bandit), builds ghcr.io/rfd-tech/payment-api and deploys to the VPS on dev push; tighten the pytest exit-code-5 allowance once real tests land.
Story | N04-2 Add /v1/health readiness probe that checks DB and Redis | PAY-N04 — Observability, Deployment & Operations | PAY-N04 | Medium | 2 | Sprint 6 | PAY-N04 phase-2 srs-should N04-2 readiness | Partial | SRS-PAY-N04 / N04-2: GET /v1/health is liveness-only and does not check DB connectivity (health.py); add a readiness endpoint that verifies the Postgres session and Redis chain store before reporting ready.
Story | N04-3 Prometheus metrics and alerts for Paystack/CALS failures and stuck pending payments | PAY-N04 — Observability, Deployment & Operations | PAY-N04 | Medium | 5 | Sprint 6 | PAY-N04 phase-2 srs-should N04-3 metrics | To Do | SRS-PAY-N04 / N04-3: No metrics are exported; add counters for initiate/confirm/fail, callback delivery outcomes, CALS relay failures, and a gauge for pending-payment age so operators can alert on stuck checkouts.
Story | N04-4 Structured request/audit logging with trace_id propagation | PAY-N04 — Observability, Deployment & Operations | PAY-N04 | Medium | 3 | Sprint 6 | PAY-N04 phase-2 srs-should N04-4 logging | Partial | SRS-PAY-N04 / N04-4: report_payment() generates a traceId for CALS events; extend structured logging across initiate and webhook handlers so a single trace_id links a payment from initiate through confirmation, callback, and CALS relay.

## Sprint Summary
Sprint | Stories | Story Points | Done | % Complete
Sprint 1 | 9 | 28 | 8 | 89%
Sprint 2 | 9 | 29 | 6 | 67%
Sprint 3 | 6 | 21 | 0 | 0%
Sprint 4 | 6 | 21 | 1 | 17%
Sprint 5 | 4 | 13 | 0 | 0%
Sprint 6 | 4 | 13 | 1 | 25%